## Defect Report - PE-16 - DF-002
Title | Register page: Password requisites not working
Description / Overview | Password requisites are not working when user is registering an account
Reproduction Steps | 1- Open the application page http://127.0.0.1:5000/
2- Click sign in
3- Click register here
4- Use pasword pass
5- Enter all test data
6- Click register
Expected Behavior | System shows error indicating wrong password format, and showing the user which are the requisites, using an example
Actual Behavior | User can register normally
Incidence / Severity / Probability of reproduction | High severity - There are no password requisites
100% reproduction rate
Story and Acceptance Criteria affected | Affected User Story: PE-16
Browsers tested | Google Chrome, v107
Environment | QA environment, http://127.0.0.1:5000/registerationForm
Notes

## Defect Report - PE-16 - DF-001
Title | Register page: Date of birth field does not exist
Description / Overview | The date of field does not exist in the register page
Reproduction Steps | 1- Open the application page http://127.0.0.1:5000/
2- Click sign in
3- Click register here
Expected Behavior | User enters all test data and the register button enables
Actual Behavior | Date of birth field does not exist
Incidence / Severity / Probability of reproduction | Medium severity - There is no age restriction
100% reproduction rate
Story and Acceptance Criteria affected | Affected User Story: PE-16
Browsers tested | Google Chrome, v107
Environment | QA environment, http://127.0.0.1:5000/registerationForm
Notes

## Defect Report - PE-53 DF-001
Title | Modify user: there is no Goverment id field
Description / Overview | When entering modify user page there is no goverment id field.
Reproduction Steps | 1- Open the application page http://127.0.0.1:5000/
2- Navigate to modify user page
Expected Behavior | Goverment id field should be available to fill.
Actual Behavior | Government field does not exist in the form available in the modify page
Incidence / Severity / Probability of reproduction | Low severity - Goverment id
100% reproduction rate
Story and Acceptance Criteria affected | Affected User Story: PE-53
Browsers tested | Google Chrome, v107
Environment | QA environment, http://127.0.0.1:5000/
Notes

## Defect Report - PE-53 DF-002
Title | Change password: allows you to change it to the current password
Description / Overview | When changing to a new password it allows the user to change to the current one
Reproduction Steps | 1- Open the application page http://127.0.0.1:5000/
2- Navigate to change password page
3- Enter the password that the user logged in already has
4- Enter all test data
5- Click save
Expected Behavior | User should get an error indicating the password they entered its the same as password they already have
Actual Behavior | Password is changed successfully
Incidence / Severity / Probability of reproduction | Low severity -
100% reproduction rate
Story and Acceptance Criteria affected | Affected User Story: PE-53
Browsers tested | Google Chrome, v107
Environment | QA environment, http://127.0.0.1:5000/
Notes